## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Mon&Tues | Wed&Thurs | Fri&Sat | Sun&Mon | Assigned to:
To Add New Stock | Inform user about capacity remaining if compartment is overfilled. | 1 |  |  |  |  | Nick
To Review Stock Changes | Implement Changes in Add Stock for picking date. | 1 |  |  |  |  | Nick
To Review Stock Changes | Verify User Filtering and Implement Date Range Filtering | 2 |  |  |  |  | Nick
To See Available Food | Implement Cook user role | 1 |  |  |  |  | Ezra
To See Available Food | Implement Stock item categories | 2 |  |  |  |  | Ezra
To See Available Food | Implement View Inventory and View Model | 3 |  |  |  |  | Ryan
To See Available Food | Implement filtering view inventory with cook role | 1 |  |  |  |  | Ryan
To Retrieve Food | Implement within inventory view remove food item | 1.5 |  |  |  |  | Ryan
To Retrieve Food | Implement stock changes log for removing food | 0.5 |  |  |  |  | Ryan
To See Available Munitions | Implement Officer user role and add munitions item category | 1.5 |  |  |  |  | Ezra
To See Available Munitions | Implement Inventory View filtering for with officer role | 0.5 |  |  |  |  | Ryan
To Retrieve munitions | Implement within inventory view remove munition item | 1 |  |  |  |  | Ryan
To Retrieve munitions | Implement stock changes log for removing munition | 0.5 |  |  |  |  | Ryan
To View Food Expiration | Implement food expiration report within view inventory for cook | 2 |  |  |  |  | Nick
To Review Stock Changes | Update Add Stock Page to Include Selection of Stock Category | 1.5 |  |  |  |  | Ezra
| Estimate Totals | 20 | 0 | 0 | 0 | 0